## Slide 1: SCM Updates [FP2020]
17 October 2014
BkkbN/UNFPA
Supply Chain Management (SCM) Models

## Slide 2
Supply Chain Management Model
Model-A
Model-B
Model-C
Strengthen current BkkbN's capacity in coordination with MOH at the district level
Strengthen current BkkbN's capacity and improve on existing SCM activities
Third party (3PL) contract to support BkkbN's SCM activities

## Slide 3
MAP of Indonesia with 34 Provinces
Pilot Intervention

## Slide 4: Goal and Objectives of Piloting SCM Models
Serve the People
Make Year-Round Availability of Contraceptives
Support National FP and RH Programs
Support National BPJS and JKN Programs
Better Coordination at all Levels
BkkbN
MOH
BPJS

## Slide 5
B
C
A

## Slide 6
C
C
A
A
B
B

## Slide 7: Pilot Districts
NTT Province
East Java Province
Pilot Districts
Pilot Districts
Control District
Control District
Kota Kupang, Kabupaten Kupang (Model A)
Sabu Raijua, Manggarai Barat (Model C)
Sikka, Sumba Barat (Model B)
Lamongan (Model A)
Pamekasan (Model B)
Banyuwangi
(Model C)
Sampang
Flores Timur & Alor
Sumbah Tengah or Manggarai Timur
Manggarai or Belu
Tuban
Pasuruan

## Slide 8: SCM Training Curriculum
Existing BkkbN’s SCM Manual
SOP of SCM Models
Additional Slides/Materials
Revised/Improved SCM Model Training Curriculum for District and Puskesmas
Partici-pants Hand Book
Refere-nce Manual
Trainer’s Guide
International Standards
Competency based

## Slide 9: SCM Model Training for Districts (3-Days) (Sessions and Time Allocated in minutes)
Pre-Test
Post-Test
Adult Learning Method
Training Evaluation
Competency based
Chart: 
| 9.Closing Session | 8.Quality Assurance, Supervision, M&E | 7.Recording and Reporting (LMIS) | 6.Distribution and Transportation | 5.Storage and Warehousing | 4.SCM-Logistics Indicators | 3.Inventory Management | 2.Introduction | 1.Opening Session
 | 105 | 120 | 195 | 45 | 105 | 60 | 150 | 105 | 60

## Slide 10: Summary: SCM TOT and Training Session Plan
SN. | Description | Main Topic Covered | Time Duration
1. | Opening Session | Registration; Introduction by participants; Objectives and Goal; Remarks by Guest; Training Rules, Selection of Reporters and Officers of a day from participants; Pre-Test | 60 min
2. | Introduction Session | Logistics Cycles; Six-Rights; Definitions; SCM Model Design; Core Activities | 105 min
3. | Inventory Management Session | Min-Max Level and EOP; Contraceptive Flow Chart; EXERCISES; Key Procedures at different levels | 150 min
4. | SCM/Logistics Indicator Session | Performance Indicators, Process Indicators, How they are measured | 60 min
5. | Storage and Warehousing Session | General principle, Useful signs in cartoons, 13-points standard storage guidelines, Disposal of expired and un-usable | 105 min
6. | Distribution and Transportation Session | Pull and Push distribution, distribution system at different levels | 45 min
7. | Recording and Reporting Session (LMIS) | Forms used for record keeping, Reporting (Practice filling up 21 Forms), Flow of Reports | 195 min
8. | QA, Supervision, M & E Session | Quality Assurance at various stages (procurement, storage, distribution, transportation);Monitoring at different levels; monitoring logistics indicators; Evaluation at different levels | 120 min
9. | Closing Session | Admin/Finance activities, Post-Test, Training Evaluation Form, Closing Remarks | 105 min

## Slide 11: Implementation and Training Plan
Curriculums
Standard Operating Procedure for Model A, B and C
Receiving, Storage, and Distribution of Contraceptives and Non-Contraceptives for National FP Program
Other Training Materials (additional Slides)
3-Days TOT (Training of Trainers) at BkkbN
Participants
BkkbN-4
MOH – 2
Province – 2
PT POS – 2
BPJS (observer)
3-Days TOT/Training at Province (NTT) (MOH, BkkbN, PTPOS, District, BPJS)
3-Days TOT/Training at Province (East Java) (MOH, BkkbN, PTPOS, District, BPJS)
3-Days Training Program at District
(SKPDKB, Puskesmas,
Dinkes, and BPJS)
3-Days Training Program at District
(SKPDKB, DinKes,
Puskemas, BPJS)
3-Days Training Program at District
(SKPDKB, PT-POS, Puskesmas,
DinKes, BPJS)
Center
Province
District
A
B
C

## Slide 12: Timeline for Piloting SCM Model Activities
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
Draft/revised SCM Training Curriculum for Model A, B and C
Mid-Term Review
Close Supervision and Monitoring
TOT/Training in District for Piloting
2014
2015
Evaluation of Pilot Districts
May
Evaluation Report and Dissemination
Collect baseline performance indicators
Client Exit Interview

## Slide 13: Twelve (12) Training Points
TOT in Center
Orientation/TOT in East Java
Orientation/TOT in NTT
Training in Lamongan [A]
Training in Banyuwangi [C]
Training in Pamekasan [B]
Training in Kota Kupang [A]
Training in Sikka [B]
Training in Sabu Raijua [C]
Training in Kabupaten Kupang [A]
Training in Sumba Barat [B]
Training in Manggarai Barat [C]
Participants | 
Total Trainees | 253
Total Trainers | 37
Total Observers | 61
Total | 351

## Slide 14: Thank You!